## Sheet1
Questionnaire within the market research phase for the planned procurements:
No | QUESTIONS OF THE CONTRACTING AUTHORITY | ANSWERS
1 | According to that the Framework agreement duration is 96 months, the price or rates should be recalculated according to the changes in the price level every year; | Yes, it is planned to be included in the contract price recalculation method to be applied. The contracting authorty welcomes the market to propose objective and adequate price indexation and recalculation mechanisms.
2 | Will design proposals be submitted with a cost-benefit analysis? | Design Proposals stage to be required by the upcoming contracts envision cost-benefit analysis to be included in the deliverable.
3 | Is the term for the expertise included in the term for the Master design preparation? | The designer should prepare the documentation in line with legal requirements to get project documentation approved by expertise. The designer should evaluate the neccasary timeline (approx 6 month period) for alignment and approval with the Client and expertise. The precise review terms and procedures shall be provided in the draft contract documentation, however, the participant should assess that documentation shall be reviewed by the Client and expertise within 30-60 day periods.
4 | In the provided documentation is specyfied the land acquisition during design. There should be no such stage in the preparation of the master design. | Taking into consideration very tight schedule of project implementation, land acquisition will be implemented in parallel to Master design. Understnading the risks that may appear doing these two processes in parallel it is planned to foresee accordingly the relevant Contract conditions which will foresee the possibility of the changes and remuneration of additional work (if such appears due to the land acquisition).
5 | The term for Master design - 24 months is not reasonable. | The prolongation of Master design preparation term is dependent on financing conditions and not possible. The award winning tenderer should have sufficient team capabilities and resources to perform neccasary services on schedule, not later then in 24 months.
6 | There must be clear criteria for the Detail design stage, as the DP stage will be prepared in the absence of the contractor, some parts of the Detail design should be adjusted after selecting the contractor. | For this reason it is planned to sign a Framework agreement and Detail design stage will be implemented after selecting the Construction contractor.
7 | How many experts will be appointed? | Preliminary planned key experts list (from Service provider side): Design manager; 1435 mm gauge railway track designer; Structural/bridge designer. Preliminary planned additional experts list: Project manager; Road design expert/engineer; Geotechnical expert/engineer; Environment expert/engineer; Hydrology expert/engineer; Building Information Modelling (BIM) Manager; Project Planning Manager; Local Stakeholder Manager; Public relations coordinator; Contract Manager; Construction planning expert/engineer; Cost estimation expert; Design Quality Control engineer; Power networks designer/engineer; Railway signalling expert/engineer; Railway catenary expert/engineer; Technical translator (from/to Lithuanian-English and English-Lithuanian language); Geographical information systems (GIS) Expert; Reliability, Availability, Maintainability, and Safety (RAMS) Engineer; Natural gas and oil pipeline expert/engineer; 1520 mm gauge railway track design expert/engineer; 1520 mm gauge railway signalling expert/engineer; Geodesy expert/engineer. Please take into account that the list of experts is not connected directly with the scope of works but with expertise requisted. To ensure the design preparartion on time (in 24 mnths period) Tenderer must ensure the needed quantity of experts and their involvement.
8 | What will be BIM level of details: whether it will be applied for the designs, which will be in a category for simple repair (for roads and its related structures - culverts and slopes). | Any newly designed infrastructure, or any affected infrastructure to be designed in 3D and have associated metadata assigned to it. Exact Level of detail as well as level of information will be provided in Employer's Information Requirements, which is a part of Design Guidelines that will be provided at the Second Stage of the procurement.
9 | How to evaluate the frequency of design supervision on the construction site? Will there be specific requirements not required for STR? | Details of the design supervision requirements will be provided at the Second stage of the procurements.
10 | There was a question about the number of experts to be involved in the process of Master Design to be ready in 24 months. Please inform how many experts will be appointed for this project from the Client's and related parties' side to ensure Master Design acceptance in 24 months period fulfilling Builder's right and accompanying obligations, approval process, expertise, project related information provision in timely manner and etc.? | The contract will foresee the term applicable to the Client for Master Design acceptance. The number of the experts from the Client side will be sufficient to ensure the implementation of the foreseen Contractual term.
11. | For the section PL/LT border-Kaunas Urban Node, the final amount of structures seems to be not clear. Will the amount of structures be clarified before submitting the final offer? If not, how changes in amount of objects to be design will be dealt with? | As explained in the presentation, this section is undergoing Special Planning procedures and the optimal alternative is not chosen yet. The procurement will not be launched until only one optimal alternative remain. The optimal alternite will have a clear number of structures defined.
12. | Will land plot acquisition be completed before Designer will start works? | No, the land acquisition will be done in parallel to Master Design preparation. Please also refer the answer to question Nr. 4
13. | We suggest to have a 80-20 (tech-financial) evaluation criteria. Can you confirm? | Thank you for your suggestion, we will consider it, and the final requirements of evaluation criteria will be provided at the Second stage of the procuements.
14. | Will contract conditions be in accordance with best practise in Western Europe for similar tenders? As to our knowledge, earlier used contract conditions where considered by Lead Consultants as not meeting usual proffesional practise and as highly risky. Number of reputable and proffesionally strong companies from Western Europe have decided not to participate in the tenders because of that. Also companies, which have strong business risk management and business integrity procedures have added significant additional margin to their fees in order to outweight at least in some extend contractual risks. Having above in mind we strongly recommend you to consider comments from large Western European Consultants, which are related to contract conditions. | It is planned to draft agreement that will be based on the templates commonly used in the industry. It is planned to include the main contract conditions, related to the high risk into the list of negotaible contracts conditions, to find the optimum business risk balance for all Contract parties. Contract conditions will be presented at the second stage of the procurement so the qualified companies will have possibility to provide their proposals/remarks to the Contract before the submission of the proposal.
15. | Will procurements have optimum balance during evaluation between financial and technical proposal? Based on results of previous tenders, we can conclude that there where too large weigth of financial proposal part and therefore winners have been awarded with price, which is significantly lower than normal price for similar services. The above have resulted in strong challanges and likely negative consequances for the Lead Consultant, its subconsultants, the Client and Beneficiaries. Having above in mind our first evulation for GO/NO GO solution before starting significantly investing in preparation of proposals will be if part in evaluation related to financial proposal is small enough for not motivating participants to damp prices down. To our knowladge, for avoiding above situations in Western Europe usual practise is that for such kind of assignments weight of Financial proposal comprises only 20%, while Technical Proposal – 80% out of total evaluation. In above case, for avoiding unreasonable escalation of proposal prices, client is setting up realistic maximum budget for services. As a result of above approach, companies are competing mainly by technical proposals. Some increase of service costs is paid to the Client and beneficiaries back by more smooth performance of the services and higher quality of services. | Thank you for your suggestion, we will consider it, and the final requirements of evaluation criteria will be provided at the Second stage of the procurements.
16. | Vilnius Urban Node and Kaunas Urban Node is excluded from the scope of upcoming procurements, so when and in what projects it will be designed? | Urban Nodes are not part of this market consultation.
17. | I want to clarify if there is no value enginering stage in these projects? What is status of environmental assesment? And it is strange 72 month duration for detailed design? Please clarify | Value Engineering will not be a stage, it is a continious activity of making a design better and the designer is involved in it throughout the entire duration of the contract. The initial design solutions shall be submitted by the designer during Design Proposals stage. Nonetheless, the designer shall undertake Value Engineering activities even after Design Proposal stage is completed. Regarding EIA - it is planned that before second stage of the procurement procedure draft EIA report will be provided to tenderers. Final approved EIA report will be provided to the winning tender after the contract signature. Regarding 72 months - first 24 months is a Master design stage to be fully completed and building permit received. The remaining Framework Agreement activities will be requested when needed and it is expected that DTD services provision may be requested up to 72 months after Framework Agreement is signed.
18. | Do these 72 months of DTD include 24 months of MD, or is it 72 months seperately from MD? | The 72 month duration is counted from the date the contract is signed. DTD services requested when needed. 72 months (DTD) include 24 months(MD).
19. | Design proposals topic, the concept. All the requirements will folow the construction law of Lithuania? Or it is planned to add additional detailed requirements? | Design Proposals requirements will be build on the basis of Lithuanian Construction Law requirements, with additional requirements listed under the contract. The Designer is expected to provide cost-benefit analysis/calculations for the elements where improvements can be made. Furthermore, it is important to note that all applicalble technical standards and RB Rail Design Guideline requirements shall be taken into account while performing the activity refered as Design Proposal in the foreseen contracts.
20. | Is there any indications to make a pause of the contract? (suspension of the contract) | Suspensions cannot be planned before contract is signed and started, but are possible. Master design will take 24 months.
| In previous RBR contracts Master and Detail technical Design stages were contractually separated, which was OK for majority of projects, however some single stage projects such as roads reconstruction did not have definition specified in a contract, which means it was not clear which requirements were set for BIM models. are you planning to change this in the new contracts? | The Client is planning to add a clause defining what level of information is requested for single stage projects, such as roads. It is expected that single stage projects will have highest detalization requirements equivalent to DTD. RB Rail sees the implementation of BIM requirements as a critical to our project. It is expected the designer will be able to apply best BIM practise and will develop fully compliant BIM models from day one, which will also include all neccasary metadata, as well as document management following common data environment approach. Furthermore, BIM requirements for major railways projects are now mandatory by Lithuanian Law.
21. | As you said that there will be one payment after the section is done, have you thougth about splitting payment for the phases, for example Master design could be splitted in phases e.g. - site investigations, design, etc. | At the moments it is planned to split payments by certain activities (site investigations, design proposals, Master Design, receival of building permit, etc.) and make payments when full scope of these activities are completed for the entire sub-section of the project. However, RBR are also investigating a possibility to further split up the payment of sub-sections into smaller construction objects if legal and financial conditions permit us to do so. The payment breakdown structure will be provided in the second stage of the procurement.
22. | In which language will be all design documentation required? And do you also foreseen any hard copies for submittions? Currently documents are prepared in parallel | It should be in two languages - both in Lithuanian and English. Design documentation should have both languages presented. Whereas, the drawings shall have bi-lingual annotations, frames, titles, etc. RB Rail does not foresee the need for document hardcopies, however a designer should be ready to issue any hard copies if these are requested from other organisations with which the project needs to be aligned with.
23. | What FIDIC book will be of the contract? | We intend to use White FIDIC as a base of our contract, specifics will be adapted to reflect the needs of our contract.
24. | Is it the main client will be RB RAIL AS or it will be a branch of any country? | It is planned the Client and the contract manager will be RB Rail AS, not a branch.
25. | During the suppliers meeting it was stated that one of the criteria for the experts will be knowledge of Lithuanian language and free communication in Lithuanian knowledge. We would like to clarify would it be the requirement for all experts or it will be enough to provide translation for the submission of the documents? From our perspective and experience, it is absolutely mandatory to have day to day communication and exchange of information in English language. | Daily communication is expected to be in English language, as it is the main language of the foreseen contract. Nevertheless, the project documentation shall be bi-lingual as the projects will have to be aligned with Lithuanian Authorities. There is no mandatory requirement for expert to have Lithuanian language skills, however translation of any technical documentation prepared by such expert shall be done by a competent technical translator, so Lithuanian Authorities could understand the technical information presented in all the documents submitted to RB Rail.