## Appendix 3 (hidden)
Agreement | ''Detailed Technical Design and Design Supervision Services for Mainline section from Riga International Airport to Misa and from Upeslejas to railway station “Rīga – Preču””
Commencement Date
No. | Railway section | Deadline (months from Commencement Date)
1. | Master Design | 6
Design piority section 3 Riga International Airport to Misa
| Building permit BP3.7 | 2
| Building permit BP3.6 | 2
| Building permit BP3.5 | 2
| Building permit BP3.3 | 3
| Building permit BP3.2 | 4
| Building permit BP3.1 | 4
| Building permit BP3.4 | 5
Design piority section 2 Upeslejas to railway station ''Rīga – Preču''
| Building permit BP2.1 | 6
| Building permit BP2.2 | 6
| Building permit BP2.3 | 6
2. | Detailed Technical Design approval before upload in Building information system | 16 | `
Design piority section 3 Riga International Airport to Misa
| Building permit BP3.7 | 7
| Building permit BP3.6 | 7
| Building permit BP3.5 | 7
| Building permit BP3.3 | 8
| Building permit BP3.2 | 11
| Building permit BP3.1 | 11
| Building permit BP3.4 | 14
Design piority section 2 Upeslejas to railway station ''Rīga – Preču''
| Building permit BP2.1 | 16
| Building permit BP2.2 | 16
| Building permit BP2.3 | 16
3. | Approved Detailed Technical Design in Building information system by State Railway Technical Inspectorate Republic o Latvia (VDzTi) | 20
Design piority section 3 Riga International Airport to Misa
| Building permit BP3.7 | 15
| Building permit BP3.6 | 15
| Building permit BP3.5 | 15
| Building permit BP3.3 | 16
| Building permit BP3.2 | 17
| Building permit BP3.1 | 17
| Building permit BP3.4 | 18
Design piority section 2 Upeslejas to railway station ''Rīga – Preču''
| Building permit BP2.1 | 20
| Building permit BP2.2 | 20
| Building permit BP2.3 | 20

## Appendix 4 (hidden)
Agreement | ''Detailed Technical Design and Design Supervision Services for Mainline section from Riga International Airport to Misa and from Upeslejas to railway station “Rīga – Preču””
Commencement Date
No. | Payment schedule per every section | Agreement stage Remuneration (EUR) | Percentage from total Remuneration for the Design Services | Evidence / Documentation for Payment in accordance with the approval procedures in the Particular Conditions
1. | Master Design |  | 35% | Provisional Delivery and Acceptance Certificate and Consultant’s invoice | Investigation
| Design piority section 3 Riga International Airport to Misa |  | 27%
| Building permit BP3.7 |  | 3% |  | x
| Building permit BP3.6 |  | 4% |  | x
| Building permit BP3.5 |  | 4%
| Building permit BP3.4 |  | 4%
| Building permit BP3.3 |  | 1%
| Building permit BP3.2 |  | 4%
| Building permit BP3.1 |  | 7%
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' |  | 8%
| Building permit BP2.1 |  | 1%
| Building permit BP2.2 |  | 4%
| Building permit BP2.3 |  | 3%
2. | Detailed Technical Design approval before upload in Building information system |  | 35%
| Design piority section 3 Riga International Airport to Misa |  | 27%
| Building permit BP3.7 |  | 3%
| Building permit BP3.6 |  | 4%
| Building permit BP3.5 |  | 4%
| Building permit BP3.4 |  | 4%
| Building permit BP3.3 |  | 1%
| Building permit BP3.2 |  | 4%
| Building permit BP3.1 |  | 7%
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' |  | 8%
| Building permit BP2.1 |  | 1%
| Building permit BP2.2 |  | 4%
| Building permit BP2.3 |  | 3%
3. | Approved Detailed Technical Design in Building information system by State Railway Technical Inspectorate Republic o Latvia (VDzTi) |  | 30%
| Design piority section 3 Riga International Airport to Misa |  | 23%
| Building permit BP3.7 |  | 2%
| Building permit BP3.6 |  | 3%
| Building permit BP3.5 |  | 4%
| Building permit BP3.4 |  | 3%
| Building permit BP3.3 |  | 1%
| Building permit BP3.2 |  | 3%
| Building permit BP3.1 |  | 7%
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' |  | 7%
| Building permit BP2.1 |  | 1%
| Building permit BP2.2 |  | 4%
| Building permit BP2.3 |  | 2%
| Total Remuneration for Design Services |  | 100%
Investiagions
DSS

## DFP 24.11.2023 (hidden)
Agreement | ''Detailed Technical Design and Design Supervision Services for Mainline section from Riga International Airport to Misa and from Upeslejas to railway station “Rīga – Preču””
Commencement Date
No. | Payment schedule per every section | Agreement stage Remuneration (EUR) | Percentage from total Remuneration for the Design Services | Evidence / Documentation for Payment in accordance with the approval procedures in the Particular Conditions
1. | Master Design |  | 35% | Provisional Delivery and Acceptance Certificate and Consultant’s invoice
| Design piority section 3 Riga International Airport to Misa |  | 27%
| Building permit BP3.7 |  | 3%
| Building permit BP3.6 |  | 5%
| Building permit BP3.5 |  | 4%
| Building permit BP3.3 |  | 4%
| Building permit BP3.2 |  | 2%
| Building permit BP3.1 |  | 3%
| Building permit BP3.4 |  | 6%
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' |  | 8%
| Building permit BP2.1 |  | 2%
| Building permit BP2.2 |  | 3%
| Building permit BP2.3 |  | 3%
2. | Detailed Technical Design approval before upload in Building information system |  | 35%
| Design piority section 3 Riga International Airport to Misa |  | 27%
| Building permit BP3.7 |  | 3%
| Building permit BP3.6 |  | 5%
| Building permit BP3.5 |  | 4%
| Building permit BP3.3 |  | 4%
| Building permit BP3.2 |  | 2%
| Building permit BP3.1 |  | 3%
| Building permit BP3.4 |  | 6%
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' |  | 8%
| Building permit BP2.1 |  | 2%
| Building permit BP2.2 |  | 3%
| Building permit BP2.3 |  | 3%
3. | Approved Detailed Technical Design in Building information system by State Railway Technical Inspectorate Republic o Latvia (VDzTi) |  | 31%
| Design piority section 3 Riga International Airport to Misa |  | 25%
| Building permit BP3.7 |  | 3%
| Building permit BP3.6 |  | 4%
| Building permit BP3.5 |  | 4%
| Building permit BP3.3 |  | 3%
| Building permit BP3.2 |  | 2%
| Building permit BP3.1 |  | 3%
| Building permit BP3.4 |  | 6%
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' |  | 6%
| Building permit BP2.1 |  | 1%
| Building permit BP2.2 |  | 3%
| Building permit BP2.3 |  | 2%
| Total Remuneration for Design Services |  | 101%
4 | Stage | New Agreement
|  | Description |  | Boreholes | Quantity | Unit | Rate | Total | Notes
First stage investigations
| Initial phase SI (1.1) Verification investigations (20% of the 1.2 scope) | Boreholes 6m |  | 26 | 156 | m |  | 0 | Works must be performed according to Annex X "Additional Requirements for Site Investigations (Geological and Hydrogeological Surveys)"
|  | Boreholes and field tests 6m |  | 27 | 162 | m |  | 0
|  | Boreholes 6-10m |  | 2 | 20 | m |  | 0
|  | Boreholes and field tests 6-10m |  | 3 | 30 | m |  | 0
|  | Boreholes and field tests 25-50m |  | 31 | 1550 | m |  | 0
| Remaining phase SI (phase 1.2) | Boreholes 6m |  | 113 | 678 | m |  | 0 | Works must be performed according to Annex X "Additional Requirements for Site Investigations (Geological and Hydrogeological Surveys)"
|  | Boreholes and field tests 6m |  | 119 | 714 | m |  | 0
|  | Boreholes 6-10m |  | 3 | 30 | m |  | 0
|  | Boreholes and field tests 6-10m |  | 6 | 60 | m |  | 0
|  | Boreholes and field tests 25-50m |  | 135 | 6750 | m |  | 0
Second stage investigations
| Second stage SI (20% of the 1.2 scope) | Boreholes 6m |  | 26 | 156 | m |  | 0 | Works must be performed according to Annex X "Additional Requirements for Site Investigations (Geological and Hydrogeological Surveys)"
|  | Boreholes and field tests 6m |  | 27 | 162 | m |  | 0
|  | Boreholes 6-10m |  | 2 | 20 | m |  | 0
|  | Boreholes and field tests 6-10m |  | 2 | 20 | m |  | 0
|  | Boreholes and field tests 25-50m |  | 31 | 1550 | m |  | 0
|  | Geophysical investigations for karst (km) |  | 2 | 20 | 100 m |  | 0
5 | Payment schedule per every section | Amount of units, days | Unit cost (excl. VAT), EUR |  | Total cost (excl. VAT), EUR
| Design piority section 3 Riga International Airport to Misa | 651.75
| Design manager |  |  | for 1 day
| Railway track designer (1435mm gauge) |  |  | for 1 day
| Bridge-structural designer |  |  | for 1 day
| Road designer |  |  | for 1 day
| Other experts |  |  | for 1 day
| Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' | 173.25
| Design manager |  |  | for 1 day
| Railway track designer (1435mm gauge) |  |  | for 1 day
| Bridge-structural designer |  |  | for 1 day
| Road designer |  |  | for 1 day
| Other experts |  |  | for 1 day
Total Remuneration for Design Services Supervision

## DFP
Annex No 4 to the Regulation for the open competition
“Detailed technical design and design supervision services for main line section from Riga International Airport to Misa and from Upeslejas to railway station “Rīga – Preču””, id. No RBR 2023/17
ANNEX NO 4: DETAILED FINANCIAL PROPOSAL
1 | Unit costs provided in the Detailed Financial Proposal for the Design Services (including On Demand Services) and Design Supervision Services shall correlate with the content information provided in Tenderer’s Technical proposal and shall represent Tenderer’s best engineering practice applied for similar service provision contracts in order to ensure proper provision of services in high quality and within the set deadlines.
2 | Amount of units specified in kilometres represents the indicative total length of the double track railway line and covers full scope of Services to be provided by the Tenderer. This amount of units is used only in the form of Detailed Financial proposal and shall not be treated as limiting and/or restricting the scope of Services.
3 | In the Detailed Financial Proposal 1 km of railway line represents an indicative 1 km of the double track railway line as a part of overall scope of Services (not limited by the position and/or layout of the any objects in relation to the railway line covered within the scope of Services).
4 | For the investigations unit costs per borehole meter in the Table 1.3. are applicable for the actual payments as well as for the future variations if needed.
5 | For the On Demand Services in the Table 1.4. completed remuneration per BP will be used.
6 | For the Design Supervision Services the total amount of days for experts must be aligned with given days for each DPS.
7 | The Total Remuneration payable for the ordered Services shall cover: -all costs and expenses that relate to performance of the ordered Services and Consultant’s obligations under the Agreement and applicable laws, including, but not limited to overheads; -travel, transport, communication and accommodation costs; -expected and unexpected (including, overtime) labour costs and costs related to engaging the personnel; - taxes and duties; - costs for insurance policies and securities; -Consultant’s additional administrative costs and profit, and remuneration for all risks, liabilities and obligations undertaken by the Consultant under this Agreement.
8 | Information shall be filled in all the designated green areas of the tables.

## DFP_DS_DSS
1. | Detailed financial proposal breakdown for the Design Services
Table 1.1. | Remuneration for the Design Services without Investigations
| No. | Item | Remuneration, EUR | Percentage from total Remuneration for the Design Service without Investigations | Evidence / Documentation for Payment in accordance with the approval procedures in the Particular Conditions
| 1 | Master Design | 0 | 35% | Provisional Delivery and Acceptance Certificate and Consultant’s invoice
|  | Design piority section 3 Riga International Airport to Misa | 0 | 27%
|  | Building permit BP3.7 | 0 | 3%
|  | Building permit BP3.6 | 0 | 5%
|  | Building permit BP3.5 | 0 | 4%
|  | Building permit BP3.3 | 0 | 4%
|  | Building permit BP3.2 | 0 | 2%
|  | Building permit BP3.1 | 0 | 3%
|  | Building permit BP3.4 | 0 | 6%
|  | Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' | 0 | 8%
|  | Building permit BP2.1 | 0 | 2%
|  | Building permit BP2.2 | 0 | 3%
|  | Building permit BP2.3 | 0 | 3%
| 2 | Detailed Technical Design approval before upload in Building information system | 0 | 35% |  |  |  | 2
|  | Design piority section 3 Riga International Airport to Misa | 0 | 27%
|  | Building permit BP3.7 | 0 | 3%
|  | Building permit BP3.6 | 0 | 5%
|  | Building permit BP3.5 | 0 | 4%
|  | Building permit BP3.3 | 0 | 4%
|  | Building permit BP3.2 | 0 | 2%
|  | Building permit BP3.1 | 0 | 3%
|  | Building permit BP3.4 | 0 | 6%
|  | Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' | 0 | 8%
|  | Building permit BP2.1 | 0 | 2%
|  | Building permit BP2.2 | 0 | 3%
|  | Building permit BP2.3 | 0 | 3%
| 3 | Approved Detailed Technical Design in Building information system by State Railway Technical Inspectorate Republic o Latvia (VDzTi) | 0 | 30%
|  | Design piority section 3 Riga International Airport to Misa | 0 | 24%
|  | Building permit BP3.7 | 0 | 3%
|  | Building permit BP3.6 | 0 | 4%
|  | Building permit BP3.5 | 0 | 4%
|  | Building permit BP3.3 | 0 | 3%
|  | Building permit BP3.2 | 0 | 2%
|  | Building permit BP3.1 | 0 | 3%
|  | Building permit BP3.4 | 0 | 5%
|  | Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' | 0 | 6%
|  | Building permit BP2.1 | 0 | 1%
|  | Building permit BP2.2 | 0 | 3%
|  | Building permit BP2.3 | 0 | 2%
|  | Remuneration for the Design Services without Investigations |  | 100%
Table 1.2. | Remuneration for the Design Services without Investigations per Building permit
| No. | Item | Remuneration, EUR
| 4 | Design piority section 3 Riga International Airport to Misa | 0
|  | Building permit BP3.7 | 0
|  | Building permit BP3.6 | 0
|  | Building permit BP3.5 | 0
|  | Building permit BP3.3 | 0
|  | Building permit BP3.2 | 0
|  | Building permit BP3.1 | 0
|  | Building permit BP3.4 | 0
|  | Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' | 0
|  | Building permit BP2.1 | 0
|  | Building permit BP2.2 | 0
|  | Building permit BP2.3 | 0
Table 1.3. | Remuneration for the Investigations according to Annex 18 "Additional Requirements for Site Investigations (Geological and Hydrogeological Surveys)"
| 5 | Item | Amount of units | Unit | Unit cost (excl. VAT), EUR | Total cost (excl. VAT), EUR
First stage investigations
Initial phase SI (1.1) Verification investigations (20% of the 1.2 scope)
|  | Boreholes 6m | 156 | m |  | 0
|  | Boreholes and field tests 6m | 162 | m |  | 0
|  | Boreholes 6-10m | 20 | m |  | 0
|  | Boreholes and field tests 6-10m | 30 | m |  | 0
|  | Boreholes and field tests 25-50m | 1550 | m |  | 0
Remaining phase SI (phase 1.2)
|  | Boreholes 6m | 678 | m |  | 0
|  | Boreholes and field tests 6m | 714 | m |  | 0
|  | Boreholes 6-10m | 30 | m |  | 0
|  | Boreholes and field tests 6-10m | 60 | m |  | 0
|  | Boreholes and field tests 25-50m | 6750 | m |  | 0
Second stage investigations
Second stage SI (20% of the 1.2 scope)
|  | Boreholes 6m | 156 | m |  | 0
|  | Boreholes and field tests 6m | 162 | m |  | 0
|  | Boreholes 6-10m | 20 | m |  | 0
|  | Boreholes and field tests 6-10m | 20 | m |  | 0
|  | Boreholes and field tests 25-50m | 1550 | m |  | 0 | `
|  | Geophysical investigations for karst (km) | 20 | 100 m |  | 0
|  | Remuneration for the Investigations |  |  |  | 0
Table 1.4. | Remuneration On Demand Services
| 6 | Item | Remuneration, EUR
Design piority section 3 Riga International Airport to Misa
Building permit BP3.7
Building permit BP3.6
Building permit BP3.5
Building permit BP3.3
Building permit BP3.2
Building permit BP3.1
Building permit BP3.4
Design piority section 2 Upeslejas to railway station ''Rīga – Preču''
Building permit BP2.1
Building permit BP2.2
Building permit BP2.3
|  | Remuneration On Demand Services | 0
Table 1.5. | Total Remuneration for the Design Services
Total cost (excl. VAT), EUR
| 7 | Remuneration for the Design Services without Investigations | 0
|  | Remuneration for the Investigations | 0
|  | Remuneration On Demand Services | 0
|  | Total Remuneration for the Design Services | 0
2. | Detailed financial proposal breakdown for the Design Supervision Services
Table 2.1. | Total Remuneration for the Design Supervision Services
| 8 | Item / Expert | Amount of units, days | Unit cost (excl. VAT), EUR |  | Total cost (excl. VAT), EUR
|  | Design piority section 3 Riga International Airport to Misa | 858 | EUR per unit | Unit
|  | Design manager |  |  | for 1 day | 0
|  | Railway track designer (1435mm gauge) |  |  | for 1 day | 0
|  | Bridge-structural designer |  |  | for 1 day | 0
|  | Road designer |  |  | for 1 day | 0
|  | Other experts |  |  | for 1 day | 0
|  | Design piority section 2 Upeslejas to railway station ''Rīga – Preču'' | 242
|  | Design manager |  |  | for 1 day | 0
|  | Railway track designer (1435mm gauge) |  |  | for 1 day | 0
|  | Bridge-structural designer |  |  | for 1 day | 0
|  | Road designer |  |  | for 1 day | 0
|  | Other experts |  |  | for 1 day | 0
|  | Total Remuneration for the Design Supervision Services |  |  |  | 0
3. | Detailed financial proposal breakdown for the Design Services and Design Supervision Services
Table 3.1. | Total Remuneration for the Design Services and Design Supervision Services
Total cost (excl. VAT), EUR
| 9 | Total Remuneration for the Design Services | 0
|  | Total Remuneration for the Design Supervision Services | 0
|  | Total Remuneration for the Design Services and Design Supervision Services | 0

## DFP_BP3.7
4. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.7
Table 4.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.7 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.7
| 1 | Project manager |  | EUR for 1km of railway line | 3.4 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 3.4 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 3.4 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 3.4 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 3.4 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 3.4 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 3.4 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 3.4 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 3.4 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 3.4 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 3.4 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 3.4 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 3.4 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 3.4 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 3.4 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 3.4 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 3.4 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 3.4 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 3.4 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 3.4 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 3.4 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 3.4 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 3.4 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 3.4 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 3.4 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 3.4 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 3.4 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 3.4 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 3.4 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 3.4 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 3.4 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 3.4 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 3.4 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 3.4 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 3.4 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 3.4 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 3.4 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 3.4 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 3.4 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 3.4 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 3.4 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 3.4 | 0
| Total Building permit BP3.7 |  |  |  |  | 0
| Costs of Total Building permit BP3.7 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 4.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.7 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.7
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Main state road A7 overpass
| 3 | Main state road A7
| 4 | Municipality road “Vārpu ceļš” overpass
| 5 | Municipality road “Vārpu ceļš”
| Total Building permit BP3.7 |  | 0
| Costs of Total Building permit BP3.7 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP3.6
5. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.6
Table 5.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.6 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.6
| 1 | Project manager |  | EUR for 1km of railway line | 4.9 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 4.9 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 4.9 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 4.9 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 4.9 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 4.9 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 4.9 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 4.9 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 4.9 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 4.9 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 4.9 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 4.9 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 4.9 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 4.9 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 4.9 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 4.9 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 4.9 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 4.9 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 4.9 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 4.9 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 4.9 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 4.9 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 4.9 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 4.9 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 4.9 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 4.9 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 4.9 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 4.9 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 4.9 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 4.9 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 4.9 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 4.9 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 4.9 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 4.9 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 4.9 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 4.9 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 4.9 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 4.9 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 4.9 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 4.9 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 4.9 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 4.9 | 0
| Total Building permit BP3.6 |  |  |  |  | 0
| Costs of Total Building permit BP3.6 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 5.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.6 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.6
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Railway bridge over Butleru stream
| 3 | Railway bridge over Ķekava river
| 4 | Railway bridge over Ķekava river by A7
| 5 | "A/C V6 (Palejas)-A/C A7" overpass over Rail Baltica
| 6 | Municipality road “A/C V6 (Palejas)-A/C A7”
| 7 | Merchant road "Balkas-Vācu kapi" overpass
| 8 | Merchant road “Balkas-Vacu kapi”
| 9 | Ecoduct over Rail Baltica railway line
| Total Building permit BP3.6 |  | 0
| Costs of Total Building permit BP3.6 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP3.5
6. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.5
Table 6.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.5 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.5
| 1 | Project manager |  | EUR for 1km of railway line | 5.2 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 5.2 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 5.2 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 5.2 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 5.2 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 5.2 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 5.2 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 5.2 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 5.2 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 5.2 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 5.2 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 5.2 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 5.2 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 5.2 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 5.2 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 5.2 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 5.2 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 5.2 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 5.2 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 5.2 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 5.2 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 5.2 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 5.2 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 5.2 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 5.2 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 5.2 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 5.2 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 5.2 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 5.2 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 5.2 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 5.2 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 5.2 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 5.2 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 5.2 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 5.2 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 5.2 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 5.2 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 5.2 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 5.2 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 5.2 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 5.2 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 5.2 | 0
| Total Building permit BP3.5 |  |  |  |  | 0
| Costs of Total Building permit BP3.5 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 6.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.5 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.5
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Railway bridge over Daugava-Misa channel
| 3 | "A/C A5-A/C V6 (Vilciņi)" overpass over Rail Baltica
| 4 | "A/C A5-A/C V6 (Vilciņi)" overpass over A5
| 5 | Municipality road “A/C A5-A/C V6 (Vilciņi)"
| 6 | Ziemeļu street
| 7 | Local state road V6 overpass
| 8 | Local state road V6
| 9 | Ecoduct over Rail Baltica and A5 (Ķekava municipality)
| 10 | Ķekava station pedestrian crossing
| 11 | Existing 330kV high voltage overhead power line crossing
| Total Building permit BP3.5 |  | 0
| Costs of Total Building permit BP3.5 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP3.4
7. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.4
Table 7.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.4 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.4
| 1 | Project manager |  | EUR for 1km of railway line | 8.5 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 8.5 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 8.5 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 8.5 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 8.5 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 8.5 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 8.5 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 8.5 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 8.5 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 8.5 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 8.5 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 8.5 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 8.5 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 8.5 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 8.5 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 8.5 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 8.5 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 8.5 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 8.5 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 8.5 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 8.5 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 8.5 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 8.5 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 8.5 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 8.5 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 8.5 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 8.5 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 8.5 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 8.5 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 8.5 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 8.5 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 8.5 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 8.5 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 8.5 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 8.5 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 8.5 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 8.5 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 8.5 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 8.5 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 8.5 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 8.5 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 8.5 | 0
| Total Building permit BP3.4 |  |  |  |  | 0
| Costs of Total Building permit BP3.4 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 7.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.4 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.4
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Railway viaduct over V13; A8; 1520mm LDz
| 3 | State local road V7 overpass
| 4 | State local road V7
| 5 | State local road V13 ramp
| 6 | State main road A8 ramp
| 7 | Ecoduct over Rail Baltica and A5 (Olaine municipality)
| 8 | Existing 110kV high voltage overhead power line crossing
| 9 | Existing 330kV high voltage overhead power line crossing
| Total Building permit BP3.4 |  | 0
| Costs of Total Building permit BP3.4 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP3.3
8. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.3
Table 8.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.3 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.3
| 1 | Project manager |  | EUR for 1km of railway line | 4.4 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 4.4 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 4.4 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 4.4 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 4.4 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 4.4 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 4.4 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 4.4 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 4.4 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 4.4 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 4.4 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 4.4 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 4.4 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 4.4 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 4.4 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 4.4 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 4.4 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 4.4 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 4.4 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 4.4 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 4.4 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 4.4 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 4.4 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 4.4 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 4.4 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 4.4 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 4.4 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 4.4 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 4.4 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 4.4 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 4.4 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 4.4 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 4.4 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 4.4 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 4.4 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 4.4 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 4.4 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 4.4 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 4.4 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 4.4 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 4.4 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 4.4 | 0
| Total Building permit BP3.3 |  |  |  |  | 0
| Costs of Total Building permit BP3.3 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 8.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.3 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.3
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Municipality road C-11 overpass over Rail Baltica
| 3 | Municipality road C-11 overpass over A5
| 4 | Municipality road C-11
| 5 | Main state road A5 overpass
| 6 | Main state road A5
| 7 | Municipality road C-40
| Total Building permit BP3.3 |  | 0
| Costs of Total Building permit BP3.3 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP3.2
9. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.2
Table 9.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.2 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.2
| 1 | Project manager |  | EUR for 1km of railway line | 1.4 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 1.4 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 1.4 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 1.4 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 1.4 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 1.4 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 1.4 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 1.4 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 1.4 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 1.4 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 1.4 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 1.4 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 1.4 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 1.4 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 1.4 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 1.4 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 1.4 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 1.4 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 1.4 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 1.4 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 1.4 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 1.4 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 1.4 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 1.4 | 0
| 25 | Contract Manager |  |  | 1.4 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 1.4 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 1.4 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 1.4 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 1.4 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 1.4 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 1.4 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 1.4 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 1.4 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 1.4 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 1.4 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 1.4 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 1.4 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 1.4 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 1.4 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 1.4 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 1.4 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 1.4 | 0
| Total Building permit BP3.2 |  |  |  |  | 0
| Costs of Total Building permit BP3.2 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 9.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.2 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.2
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | P132 North ramp overpass over Rail Baltica
| 3 | P132 overpass over Rail Baltica and A5
| 4 | P132 South ramp overpass over Rail Baltica
| 5 | Regional state road P132
| 6 | Municipality road C-40
| 7 | Jaunmārupe station pedestrian crossing
| Total Building permit BP3.2 |  | 0
| Costs of Total Building permit BP3.2 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP3.1
10. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP3.1
Table 10.1. | Total Remuneration for the Design Services without Investigations of Building permit BP3.1 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP3.1
| 1 | Project manager |  | EUR for 1km of railway line | 4.1 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 4.1 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 4.1 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 4.1 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 4.1 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 4.1 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 4.1 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 4.1 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 4.1 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 4.1 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 4.1 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 4.1 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 4.1 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 4.1 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 4.1 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 4.1 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 4.1 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 4.1 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 4.1 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 4.1 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 4.1 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 4.1 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 4.1 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 4.1 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 4.1 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 4.1 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 4.1 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 4.1 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 4.1 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 4.1 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 4.1 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 4.1 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 4.1 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 4.1 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 4.1 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 4.1 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 4.1 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 4.1 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 4.1 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 4.1 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 4.1 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 4.1 | 0
| Total Building permit BP3.1 |  |  |  |  | 0
| Costs of Total Building permit BP3.1 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 10.2. | Total Remuneration for the Design Services without Investigations of Building permit BP3.1 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP3.1
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | RIX railway viaduct (closing span)
| 3 | Railway viaduct over aircraft path
| 4 | Municipality road C-10 underpass under Rail Baltica
| 5 | Municipality road C-10
| 6 | Municipality road C-40
| Total Building permit BP3.1 |  | 0
| Costs of Total Building permit BP3.1 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP2.3
11. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP2.3
Table 11.1. | Total Remuneration for the Design Services without Investigations of Building permit BP2.3 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP2.3
| 1 | Project manager |  | EUR for 1km of railway line | 2.7 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 2.7 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 2.7 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 2.7 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 2.7 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 2.7 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 2.7 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 2.7 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 2.7 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 2.7 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 2.7 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 2.7 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 2.7 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 2.7 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 2.7 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 2.7 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 2.7 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 2.7 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 2.7 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 2.7 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 2.7 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 2.7 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 2.7 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 2.7 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 2.7 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 2.7 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 2.7 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 2.7 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 2.7 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 2.7 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 2.7 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 2.7 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 2.7 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 2.7 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 2.7 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 2.7 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 2.7 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 2.7 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 2.7 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 2.7 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 2.7 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 2.7 | 0
| Total Building permit BP2.3 |  |  |  |  | 0
| Costs of Total Building permit BP2.3 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 11.2. | Total Remuneration for the Design Services without Investigations of Building permit BP2.3 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP2.3
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Railway viaduct over 1520mm (Rīga-Preču stacija)
| 3 | Heating utility tunnel under RB and 1520mm railways
| 4 | Railway line (gauge 1520mm) reconstruction
| Total Building permit BP2.3 |  | 0
| Costs of Total Building permit BP2.3 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP2.2
12. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP2.2
Table 12.1. | Total Remuneration for the Design Services without Investigations of Building permit BP2.2 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP2.2
| 1 | Project manager |  | EUR for 1km of railway line | 5.06 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 5.06 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 5.06 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 5.06 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 5.06 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 5.06 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 5.06 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 5.06 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 5.06 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 5.06 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 5.06 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 5.06 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 5.06 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 5.06 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 5.06 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 5.06 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 5.06 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 5.06 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 5.06 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 5.06 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 5.06 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 5.06 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 5.06 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 5.06 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 5.06 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 5.06 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 5.06 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 5.06 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 5.06 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 5.06 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 5.06 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 5.06 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 5.06 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 5.06 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 5.06 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 5.06 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 5.06 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 5.06 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 5.06 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 5.06 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 5.06 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 5.06 | 0
| Total Building permit BP2.2 |  |  |  |  | 0
| Costs of Total Building permit BP2.2 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 12.2. | Total Remuneration for the Design Services without Investigations of Building permit BP2.2 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP2.2
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Acone Pedestrian Crossing
| 3 | Pedestrian crossing of road “Pļaviņas-Raugas”
| 4 | Piķurga river animal crossing
| 5 | Railway line (gauge 1520mm) reconstruction
| 6 | TEC-2 pedestrian crossing
| Total Building permit BP2.2 |  | 0
| Costs of Total Building permit BP2.2 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_BP2.1
13. | Detailed financial proposal breakdown for the Design Services without Investigations of Building permit BP2.1
Table 13.1. | Total Remuneration for the Design Services without Investigations of Building permit BP2.1 per Experts
| No. | Experts | Unit cost (excl. VAT), EUR |  | Amount of units, km | Total cost (excl. VAT), EUR
|  | Key experts |  |  |  | Building permit BP2.1
| 1 | Project manager |  | EUR for 1km of railway line | 1.55 | 0
| 2 | Design manager |  | EUR for 1km of railway line | 1.55 | 0
| 3 | Railway track designer (1435mm gauge) |  | EUR for 1km of railway line | 1.55 | 0
| 4 | Bridge designer |  | EUR for 1km of railway line | 1.55 | 0
| 5 | Road designer |  | EUR for 1km of railway line | 1.55 | 0
| 6 | Land Amelioration Designer |  | EUR for 1km of railway line | 1.55 | 0
Additional experts (as indicated in Technical Specification)
| 7 | Track & Alignment design team (1435mm gauge) |  | EUR for 1km of railway line | 1.55 | 0
| 8 | Track & Alignment design team (1520mm gauge) |  | EUR for 1km of railway line | 1.55 | 0
| 9 | Structures design team |  | EUR for 1km of railway line | 1.55 | 0
| 10 | Hydrology and drainage design team |  | EUR for 1km of railway line | 1.55 | 0
| 11 | Geotechnical team |  | EUR for 1km of railway line | 1.55 | 0
| 12 | Geodesy experts/engineers |  | EUR for 1km of railway line | 1.55 | 0
| 13 | Railway sub-systems design team (1520mm gauge) |  | EUR for 1km of railway line | 1.55 | 0
| 14 | Railway sub-systems design team (1435mm gauge) |  | EUR for 1km of railway line | 1.55 | 0
| 15 | Road design team |  | EUR for 1km of railway line | 1.55 | 0
| 16 | Drainage design team |  | EUR for 1km of railway line | 1.55 | 0
| 17 | Public utilities design team. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  | EUR for 1km of railway line | 1.55 | 0
| 18 | Construction planning expert/engineer |  | EUR for 1km of railway line | 1.55 | 0
| 19 | Cost estimation expert |  | EUR for 1km of railway line | 1.55 | 0
| 20 | System Engineering Manager |  | EUR for 1km of railway line | 1.55 | 0
| 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  | EUR for 1km of railway line | 1.55 | 0
| 22 | Verification manager |  | EUR for 1km of railway line | 1.55 | 0
| 23 | Requirements manager |  | EUR for 1km of railway line | 1.55 | 0
| 24 | Configuration manager |  | EUR for 1km of railway line | 1.55 | 0
| 25 | Contract Manager |  | EUR for 1km of railway line | 1.55 | 0
| 26 | Project Planning Manager |  | EUR for 1km of railway line | 1.55 | 0
| 27 | Stakeholder Manager / Public relations coordinator |  | EUR for 1km of railway line | 1.55 | 0
| 28 | Design Quality Control engineer |  | EUR for 1km of railway line | 1.55 | 0
| 29 | Geographical information systems (GIS) Expert |  | EUR for 1km of railway line | 1.55 | 0
| 30 | Technical translators (from/to Latvian-English language) |  | EUR for 1km of railway line | 1.55 | 0
| 31 | Land Acquisition expert |  | EUR for 1km of railway line | 1.55 | 0
| 32 | Environment experts team All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  | EUR for 1km of railway line | 1.55 | 0
| 33 | Noise & Vibration expert |  | EUR for 1km of railway line | 1.55 | 0
| 34 | Cultural heritage expert, |  | EUR for 1km of railway line | 1.55 | 0
| 35 | Deforestation expert (to prepare deforestation plans), |  | EUR for 1km of railway line | 1.55 | 0
| 36 | Stations Design expert |  | EUR for 1km of railway line | 1.55 | 0
| 37 | Spatial planning expert / Architect |  | EUR for 1km of railway line | 1.55 | 0
| 38 | Tunnel expert |  | EUR for 1km of railway line | 1.55 | 0
| 39 | Interface manager |  | EUR for 1km of railway line | 1.55 | 0
| 40 | BIM Coordination team |  | EUR for 1km of railway line | 1.55 | 0
| 41 | Demolitions (experts for different structure and building demolishing designs), temporary works and construction process |  | EUR for 1km of railway line | 1.55 | 0
| 42 | Other experts |  | EUR for 1km of railway line | 1.55 | 0
| Total Building permit BP2.1 |  |  |  |  | 0
| Costs of Total Building permit BP2.1 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  |  |  |  | 0
Table 13.2. | Total Remuneration for the Design Services without Investigations of Building permit BP2.1 per Structures
| No | Structures | Cost per structure (excl. VAT), EUR | `
Building permit BP2.1
| 1 | Rail Baltica railway (including related infrastructure - utilities, access roads, affected existing streets and roads, maintenance roads, etc.) | 0 | `
| 1.1. | Rail Baltica railway (including maintenance roads)
| 1.2. | Roads - access roads, affected existing streets and roads, etc.
| 1.3. | Utilities.
| 2 | Saurieši station pedestrian crossing
| 3 | Road P5 overpass over RB and 1520mm railways
| 4 | State regional road P5
| 5 | Railway line (gauge 1520mm) reconstruction
| Total Building permit BP2.1 |  | 0
| Costs of Total Building permit BP2.1 shall comply with Table 1.2. "Remuneration for the Design Services without Investigations per Building permit" |  | 0
Total
#REF!
#REF!
#REF!
#REF!
#REF! |  | `
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_DPS3
| 14. | Detailed financial proposal breakdown for the Design Services in DPS3 without Investigations
| Table 14.1. | Total Remuneration for the Design Services in DPS3 without Investigations
|  | No. | Expert description | Number of experts | Days | Avarege Daily cost (excl. VAT), EUR | Total cost (excl. VAT), EUR
|  |  | Key experts | DPS3
|  | 1 | Project manager | 1 |  |  | 0
|  | 2 | Design manager | 1 |  |  | 0
|  | 3 | Railway track designer (1435mm gauge) | 1 |  |  | 0
|  | 4 | Bridge designer | 1 |  |  | 0
|  | 5 | Road designer | 1 |  |  | 0
|  | 6 | Land Amelioration Designer | 1 |  |  | 0
Additional experts (as indicated in Technical Specification)
|  | 7 | Track & Alignment design expert (1435mm gauge) |  |  |  | 0
|  | 8 | Track & Alignment design expert (1520mm gauge) |  |  |  | 0
|  | 9 | Structures design expert |  |  |  | 0
|  | 10 | Hydrology and drainage design expert |  |  |  | 0
|  | 11 | Geotechnical expert |  |  |  | 0
|  | 12 | Geodesy expert |  |  |  | 0
|  | 13 | Railway sub-systems design expert (1520mm gauge) |  |  |  | 0
|  | 14 | Railway sub-systems design expert (1435mm gauge) |  |  |  | 0
|  | 15 | Road design expert |  |  |  | 0
|  | 16 | Drainage design expert |  |  |  | 0
|  | 17 | Public utilities design expert. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  |  |  | 0
|  | 18 | Construction planning expert/engineer |  |  |  | 0
|  | 19 | Cost estimation expert |  |  |  | 0
|  | 20 | System Engineering Manager |  |  |  | 0
|  | 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  |  |  | 0
|  | 22 | Verification manager |  |  |  | 0
|  | 23 | Requirements manager |  |  |  | 0
|  | 24 | Configuration manager |  |  |  | 0
|  | 25 | Contract Manager |  |  |  | 0
|  | 26 | Project Planning Manager |  |  |  | 0
|  | 27 | Stakeholder Manager / Public relations coordinator |  |  |  | 0
|  | 28 | Design Quality Control engineer |  |  |  | 0
|  | 29 | Geographical information systems (GIS) Expert |  |  |  | 0
|  | 30 | Technical translator (from/to Latvian-English language) |  |  |  | 0
|  | 31 | Land Acquisition expert |  |  |  | 0
|  | 32 | Environment expert All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  |  |  | 0
|  | 33 | Noise & Vibration expert |  |  |  | 0
|  | 34 | Cultural heritage expert |  |  |  | 0
|  | 35 | Deforestation expert (to prepare deforestation plans), |  |  |  | 0
|  | 36 | Stations Design expert |  |  |  | 0
|  | 37 | Spatial planning expert / Architect |  |  |  | 0
|  | 38 | Tunnel expert |  |  |  | 0
|  | 39 | Interface manager |  |  |  | 0
|  | 40 | BIM Coordination expert |  |  |  | 0
|  | 41 | Demolitions (expert for different structure and building demolishing designs), temporary works and construction process |  |  |  | 0
|  | 42 | Other expert |  |  |  | 0
|  |  | Total DPS3 |  |  |  | 0
|  | Costs of Total DPS3 shall comply with Table 1.2. "Design piority section 3 Riga International Airport to Misa" |  |  |  |  | 0
The above costs for experts are based on a 8hrs day and include for all costs to the Consultant including basic salary, any additional payments or benefits and social costs such as insurances or pension payments. Office expenses, including rental and heating, non-recoverable staff time and administrative staff who are not chargeable, together with the Consultant’s general overheads and profit.
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## DFP_DPS2 BP2.1.-BP2.3.
| 15. | Detailed financial proposal breakdown for the Design Services in DPS2 BP2.1-BP2.3 without Investigations
| Table 15.1. | Total Remuneration for the Design Services in DPS2 BP2.1-BP2.3 without Investigations
|  | No. | Expert description | Number of experts | Days | Avarege Daily cost (excl. VAT), EUR | Total cost (excl. VAT), EUR
|  |  | Key experts | DPS2 BP2.1-BP2.3
|  | 1 | Project manager | 1 |  |  | 0
|  | 2 | Design manager | 1 |  |  | 0
|  | 3 | Railway track designer (1435mm gauge) | 1 |  |  | 0
|  | 4 | Bridge designer | 1 |  |  | 0
|  | 5 | Road designer | 1 |  |  | 0
|  | 6 | Land Amelioration Designer | 1 |  |  | 0
Additional experts (as indicated in Technical Specification)
|  | 7 | Track & Alignment design expert (1435mm gauge) |  |  |  | 0
|  | 8 | Track & Alignment design expert (1520mm gauge) |  |  |  | 0
|  | 9 | Structures design expert |  |  |  | 0
|  | 10 | Hydrology and drainage design expert |  |  |  | 0
|  | 11 | Geotechnical expert |  |  |  | 0
|  | 12 | Geodesy expert |  |  |  | 0
|  | 13 | Railway sub-systems design expert (1520mm gauge) |  |  |  | 0
|  | 14 | Railway sub-systems design expert (1435mm gauge) |  |  |  | 0
|  | 15 | Road design expert |  |  |  | 0
|  | 16 | Drainage design expert |  |  |  | 0
|  | 17 | Public utilities design expert. All certified/licensed designers/experts to reconstruct all Affected parties’ utilities (e.g. gas supply networks, heat supply networks, water supply networks, canalization networks, communication cables, drainage systems etc.) |  |  |  | 0
|  | 18 | Construction planning expert/engineer |  |  |  | 0
|  | 19 | Cost estimation expert |  |  |  | 0
|  | 20 | System Engineering Manager |  |  |  | 0
|  | 21 | Reliability, Availability, Maintainability, and Safety (RAMS) Engineer |  |  |  | 0
|  | 22 | Verification manager |  |  |  | 0
|  | 23 | Requirements manager |  |  |  | 0
|  | 24 | Configuration manager |  |  |  | 0
|  | 25 | Contract Manager |  |  |  | 0
|  | 26 | Project Planning Manager |  |  |  | 0
|  | 27 | Stakeholder Manager / Public relations coordinator |  |  |  | 0
|  | 28 | Design Quality Control engineer |  |  |  | 0
|  | 29 | Geographical information systems (GIS) Expert |  |  |  | 0
|  | 30 | Technical translator (from/to Latvian-English language) |  |  |  | 0
|  | 31 | Land Acquisition expert |  |  |  | 0
|  | 32 | Environment expert All certified/licensed experts in the related field of environment issue (e.g. mammal monitoring, species and habitat protection experts, noise expert etc.) assessment, investigations, monitoring and consultations as required in the environment requirements. |  |  |  | 0
|  | 33 | Noise & Vibration expert |  |  |  | 0
|  | 34 | Cultural heritage expert |  |  |  | 0
|  | 35 | Deforestation expert (to prepare deforestation plans), |  |  |  | 0
|  | 36 | Stations Design expert |  |  |  | 0
|  | 37 | Spatial planning expert / Architect |  |  |  | 0
|  | 38 | Tunnel expert |  |  |  | 0
|  | 39 | Interface manager |  |  |  | 0
|  | 40 | BIM Coordination expert |  |  |  | 0
|  | 41 | Demolitions (expert for different structure and building demolishing designs), temporary works and construction process |  |  |  | 0
|  | 42 | Other expert |  |  |  | 0
|  |  | Total DPS2 BP2.1-BP2.3 |  |  |  | 0
|  | Costs of Total DPS2 BP2.1-BP2.3 shall comply with Table 1.2. "'Design piority section 2 Upeslejas to railway station ''Rīga – Preču''" |  |  |  |  | 0
The above costs for experts are based on a 8hrs day and include for all costs to the Consultant including basic salary, any additional payments or benefits and social costs such as insurances or pension payments. Office expenses, including rental and heating, non-recoverable staff time and administrative staff who are not chargeable, together with the Consultant’s general overheads and profit.
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
Total
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!